## Summary
SPZ Documents
Project: SWIPEJOB
Contact : Kyle + Alson - SPZ Singapore
Contact : Thanh P - SPZ VietNam
Project scope: Web base ; iOS app; Android App; Web Backend
Start: |  | End: | 2016-11-20
Resource Pickup:
No. | Name | Task
1 | Thanh Pham
2 | Nhung Bui | Designer
3 | Hieu | Website + BackEnd
4 | Name | iOS app
5 | Kien | Android
Main Structure: |  |  | Timeline | iOS |  | Android
No. | Role | Description | Web ¦ Back End | Simple Demo | Connect Data | Simple Demo | Connect Data
1 | Guest |  |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Search Job |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | View Job Detail (limitted) |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
2 | Job Seeker |  |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Dashboard | 2016-10-28 | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Search Job |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | View Detail (full) |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Apply Job |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
3 | Employer |  |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Dashboard | 2016-10-28 | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Post Job |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
|  | Sent invitation () |  | 2016-11-03 | 2016-11-20 | 2016-11-03 | 2016-11-20
4 | Admin
|  | Dashboard | 2016-11-03
Setting

## Web
No. | Page Name - Role | Description | Action | Timeline | Status | Priority
1 | Login Page - Job Seeker | • When selecting “Job Seeker” option from Home menu, the Login screen is displayed to require login or register an account. • Fields: Email(username), Password • Buttons: Login, Remember Me, Forgot password, Register | Click Login, system will check account is valid or not Jobseeker can log in with Facebook option Click “Forgot password” will show next screen to enter username(email) to be received an email for changing password Select “Keep me signed in” to keep the loging Click Register if user does not have an account. |  | done
2 | Register Page - Job Seeker | • Register screen for JobSeeker with all fields as design • Buttons: Register | Guest click Sign Up to register an account After submitting successfully, go to the registered email and click on an activation link to active account Guest can also register with Facebook option |  | done
3 | Register Page - With Facebook Google - Job Seeker | • After Jobseeker logged in the FB successfully, this screen will be displayed to enter NRIC type/number • Fields: all fields should be as the design • Buttons: Sign Up | Full name and Email will get from FB Jobseeker needs to provide NRIC number/type Then click Sign Up to complete and access the app |  | done
| Dashboard - Job Seeker | This is home page when jobseeker logged in. this page as summary sheet with fill by: list all job saved, all job applied, all job skip which can link to detail. Included message, notify link to profile view/ update | follow mockup |  |  | 1
| List Job - Job Seeker | • All fields and info should be displayed as design | JobSeeker can Search jobs, Apply job , Save job or Share job Click on a job to view more details |  | done
| Job Detail - Job Seeker | • Job details screen will be displayed when JobSeeker clicks on a job to view in more details • All fields and buttons as design | Click Apply/ Save button to apply/ or save that job Click “f” button to share via Facebook Click “Email” button to share via email |  | done
| Saved Job - Job Seeker | • This screen will be displayed when JobSeeker clicks on “Saved Jobs” from left menu. • The screen shows all saved jobs- default sort on descending by posted date | Click button Delete if want to delete a job from saved list Click button Apply if want to apply that job Click on a job to view more details. |  | done
| Applied Job - Job Seeker | • This screen will show status of all applied jobs • All job statuses in this screen are “Pending Approval”, “Accepted”, “Rejected” • Default sort on Descending by Applied Date | JobSeeker access to “Applied Jobs” to view statuses of job (Pending Approval or Accepted or Rejected) Click on a job to view more details or Share job JobSeeker can click View Message to view message logs from employer (if any) for accepted job |  | done
| Message - Mail box - Job Seeker | The message log screen will be displayed when Jobseeker clicks on a new message from the message list in previous screen | In this screen, Jobseeker can view interview inviation and can reply to Employer by accept button. |  |  | 1
| Profile - Job Seeker | Show profiles / update profiles by sector |  |  | done
| Login - Employer | • When selecting “Employer” option from Home menu, the Login screen is displayed to require login or request an account. • Fields: Email(username), Password • Buttons: Login, Remember Me, Forgot password, Request an Account, “Call our hotline” | Click Login, system will check account is valid or not Click “Forgot password” will show next screen to enter username(email) to be received an email for changing password Select “Remember me” to keep the loging Click “Request an account “ if user does not have an account. |  | done
| Request Account - Employer |  |  |  | done
| Dashboard - Employer | Show as summary sheet: job post, list job seeker applied, shorted candidates, sent interview invitation Each item can link to detail. Ex: can view job seeker profiles when click on name on list --> open new window show job seeker profile | note: 1 Employer can have 1 main account and sub account inside, with this type of Employer, the main account dashboard must collect activities of member and show as summary sheet |  |  | 1
| Create new post job - Employer | all field as mockup |  |  | done

## BackEnd
No. | Page Name - Role | Description | Action | Timeline | Status | Priority
1 | Dashboard - Admin | Sumarry all : job seeker list, employer list with status. Each item can link to detail by open pop up. Can search, sort , active/deactive jobseeker, active/deactive employer account; list all request for employer account and approval by active. |  |  |  | 1
| Setting - Admin | Export to csv |  |  |  | 1

## M-App
note:
các hình thức khi chuyển màn hình + đóng pop up, summit cho pop up thông báo. Các bạn xem như thế nào là tiện lợi cho người dùng --> thống nhất trên 2 phiên bản nhé. Phần nào cần đặc biệt hơn sẽ được mô tả bên Action
tất cả các button X trong sign up/ login đều chuyển về màn hình job list - guest
No. | Page Name - Role | Description | Action | Timeline | Status
| Install App - User | Request to access: Identity, Contact, Photos, Camera, FaceBook, Gmail … | use OS default
| First view - List Job - Guest | This Mobile App (Android & IOS) is used for JobSeeker / Employer who wants to find/post a job. Some main behavior of JobSeeker as: Swipe Right to save job, swipe left to skip job ...can be save as guest activities and auto map to Job seeker dashboard when that user (on mobile devices) register account. | vuốt trái, phải một job trên joblist sẽ save vào temporary profiles của guest. Sau khi khách thoát ứng dụng, thông báo khách nên login hoặc sign up để lưu lại.Khi dùng pop up thông báo, theo font + font color của thiết kế.
| Login - Job Seeker | JS can login by Facebook, Google and Mail register | JS đăng kí không theo Facebook/ G sẽ có thể đăng nhập được bằng Email hoặc NRIC + password. Nếu đăng nhập bằng Facebook --> theo mặc định của OS. Sau khi đăng nhập tạm thời chuyển về màn hình Job List - Tab: All
| Register Account - Job Seeker | - Facebook - Google - Mail all step need verify NRIC number (now just scan the format follow open nric) | -Facebook + Google: default OS process. Khi JS login chọn login bằng facebook/G --> load theo default của os --> thoát hộp thoại facebook/ google --> load thông tin: full name, birtday, email (+ sign up bị visible )sau đó cho người dùng tiếp tục nhập NRIC, xác thực chuỗi NRIC (fomat: link sau) ( nếu chuỗi OK--> đổi màu hộp thoại sang green và hiện nút Sign up. Nếu ko đúng, đổi màu sang đỏ; button X : đóng và chuyển màn hình về list job- guest).
Dashboard - Job Seeker
| Dashboard - Job Seeker | - applied job - saved job - shortlisted job - Message list (from Employer sent for interview invitation)
| List job - Job seeker |  | vuốt trái qua phải trên job --> Saved Job; giữ nguyên vị trí job phía trên--> đẩy job phía dưới lên. Tương tự vuốt từ phải qua trái trên job --> skip job (giống swipe). User touch một job --> job detail. All + Focus : tab --> Khi người dùng vuốt từ trên -->dưới: hiển thị, nếu hết list --> reload / load update. ; ngược lại, vuốt từ dưới lên: ẩn. Focus = Filter job dựa trên profile người dùng.
| Detail Job - Job seeker |  | swipe left(right to left): load detail của job khác liền kề phía trước trong job list đang có (job list in currently). Swipe right(left to right): load detail của job khác liền kề phía sau trong job list hiện tại. Button "Case" load 2 button khác: Save và Apply
Profile - Job Seeker
| Login - Employer |  | từ màn hình guest--> login --> employer --> hiển thị màn hình login --> Login chuyển về màn hình dashboard Employer. Login fail: hiện thông báo thông tin đăng nhập ko đúng bằng pop up: cho phép tắt pop up khi user touch bất kì trên màn hình.
| Request Account - Employer |  | - từ màn hình list job của guest --> login --> employer --> màn hình yêu cầu tài khoản của empoyer. Summit hiện thông báo bằng pop up ¦ dialog: "Your request have been submitted, you will be contact in the next working day". Pop up¦ Dialog có thể được tắt khi người dùng touch lên phần còn lại của màn hình hoặc tự động chuyển về màn hình list job của guest.
| Dashboard - Employer | -remaining credit - active job list - all post job - all jobseeker applied to job --> short list --> approval and send interview invitation (just send static message and show list if candidate reply by Accept schedule)
Create Post Job - Employer
Profile - Employer