## Issues Log
Jannpaul Mobile App Issues Log
Issue No. | Date Reported | Reported By | Module | Issue/ Request Description | CR | Status | Progress/ Resolution | Priority | Responsible by | Delivery Date | Link to Images
1 | 2016-04-04 | Manfred | iOS | Homepage - 4 Diamonds sizing |  | Finished | Will be updated with the image from the App_v3.psd. Actually, these the pictures we get from your previous web site. | High | SPZ | 2016-04-08
2 | 2016-04-04 | Manfred | iOS | Homepage - Centralise bottom wordings |  | Finished | With the iPhone 4, the screen is small and the text will be cut. Please confirm. If yes, it will be done. | High | SPZ | 2016-04-08
3 | 2016-04-04 | Manfred | iOS | Choose Setting - Bigger main pic |  | Finished | Will be updated | High | SPZ | 2016-04-08
4 | 2016-04-04 | Manfred | iOS | Choose Setting - Smaller words |  | Finished | Will be updated | High | SPZ | 2016-04-08
5 | 2016-04-04 | Manfred | iOS | Choose Setting - Centralise bottom wording |  | Finished | Will be updated | High | SPZ | 2016-04-08
6 | 2016-04-04 | Manfred | iOS | Choose Setting 2 - Empty space on top |  | Finished | Will be updated | High | SPZ | 2016-04-08
7 | 2016-04-04 | Manfred | iOS | Choose Setting 2 - Smaller words |  | Finished | Will be updated | High | SPZ | 2016-04-08
8 | 2016-04-04 | Manfred | iOS | Choose Setting 2 - Remove everything below "contact us" box |  | Finished | Will be updated | High | SPZ | 2016-04-08
9 | 2016-04-05 | Manfred | iOS | Choose Setting 2 - Allow user to choose other diamond cuts |  | Finished | The system works properly for this point. For the current ring, if you define in the back-end only 1 diamond cut, it will show only 1. Whatever number of diamond cut you make (varians) for this ring, this context shows all. It makes the easy way for the end-user, if you show all types of diamond cuts anytime, but the ring’s variant just have 1 cut, and it will show (NOT FOUND) and empty space for this case if the user choosed another kind of cut. Are you going to do that? Please ocnfirm. | High
10 | 2016-04-04 | Manfred | iOS | Confirm pinch & zoom tutorial - include dismiss button |  | Finished | Normally, modern app does not include dismiss button. User tap anywhere then the tutorial image will be gone. To prevent wating time, please send us the place of the dismiss button you want. It is not included in the App_v3.psd. Notes: This request is out of the mockup EDD. Will not be handled in this phase. | High | SPZ | 2016-04-08
11 | 2016-04-04 | Manfred | iOS | Try it on - Make hand outline darker |  | Finished | Darker or thicker? Or both? here you want darker, in the ppt file you wrote thicker. Please confirm. | High | SPZ | 2016-04-08
12 | 2016-04-04 | Manfred | iOS | After taking picture - Ring position & size to follow hand outline |  | Finished | Different size of screen will have the different hand path location. We could not do that in the basic way. If you really want it, we will use the Computer Vision technology to detect the location of the ring finger, exactly the position of the place people wears ring. Not included in this phase. | High | SPZ | 2016-04-08
13 | 2016-04-04 | Manfred | iOS | After taking picture - Default view to include Selections |  | Finished | Will be updated | High | SPZ | 2016-04-08
14 | 2016-04-04 | Manfred | iOS | After taking picture Selections - Shift diamond cut images lower (even out) |  | Finished | Will be updated | High | SPZ | 2016-04-08
15 | 2016-04-04 | Manfred | iOS | After taking picture TICK - No buttons, just alert |  | Finished | Will be updated | High | SPZ | 2016-04-08
16 | 2016-04-04 | Manfred | iOS | After taking picture TICK - Change message to "The image has been saved in your camera roll" |  | Finished | Will be updated | High | SPZ | 2016-04-08
17 | 2016-04-04 | Manfred | iOS | Save button - Change "Later" to "Saved Rings" (access saved rings page) |  | Finished | Where are they? Since you asked to remove the 2 buttons on the alert message. Please confirm. | High | SPZ | 2016-04-08
18 | 2016-04-04 | Manfred | iOS | Save button - Change message to "Share your image!" |  | Finished | Will be updated | High | SPZ | 2016-04-08
19 | 2016-04-04 | Manfred | iOS | Ring size - Change to drop down list |  | Pending | Where is it? It could not be found in the ppt file. Please explain more details. | High | SPZ | 2016-04-08
20 | 2016-04-04 | Manfred | iOS | JP Unique Series - Make title header bigger |  | Finished | Will be updated | High | SPZ | 2016-04-08
21 | 2016-04-04 | Manfred | iOS | JP Unique Series - Change Page 1 of 3 to 1/3,2/3, 3/3 |  | Finished | Will be updated | High | SPZ | 2016-04-08
22 | 2016-04-04 | Manfred | iOS | JP Unique Series - default view for left/right to set at the TOP |  | Pending | Please explain more details. Could not be found in the ppt file. | High | SPZ | 2016-04-08
23 | 2016-04-04 | Manfred | iOS | Contact Us - Centralise Positioning |  | Finished | Will be updated | High | SPZ | 2016-04-08
24 | 2016-04-04 | Manfred | iOS | Change all footer with contact info. To "CONTACT US" button |  | Pending | Which footers? Please explain for more details. | High | SPZ | 2016-04-08
25 | 2016-04-04 | Thang Hong | iOS | Share button (after take hand picture) takes very long waiting time of sharing process. Suggest to follow the method "Save & Share" on Choose Your Setting Page |  | Pending | The app need time to upload the image to be shared. If you want it faster, I will compress the picture with lower quality to make it smaller. | High | SPZ | 2016-04-08
26 | 2016-04-04 | Thang Hong | Backend | Dashboard and Activities does not work |  | Pending | Please expain more details. Which information not work? Or everything not work? Or just some? | Medium | SPZ | 2016-04-08
27 | 2016-04-11 | JP | Mobile App | Alignment: The "Try It On" is at the 3/4 page but what we want is at the bottom portion. Can it be fixed position which means that regardless of how many wordings for description we have it will remain in that position. |  | Pending | This is a scrollable page, with the height can be extended or shrinked depends on the Content. The flexible content's height is because of the description & the title. Right now, the data in the system has no description, so it look different from the PSD mockup. If you want the button is aligned at the bottom of the screen, think of the iPad and it is horrible. In case the iPhone 4s is used, with the long description, the text will be cut-off. So, again, this screen must be scrollable, and the button is closed to the content. |  |  |  | Images!A15
28 | 2016-04-11 | JP | Mobile App | Alignment: The "Explorer" & "Try it On" there is a huge blank space between that and the wordings at the bottom. |  | Finished | It should be like that, because for the taller / shorter screens, the space between the button Try It On and the bottom text will be expanded or scaled down. Also, the bottom text should be aligned at the bottom, similar to the footer. [Thang Hong – 17th April] Already explained to client |  |  |  | Images!A47
29 | 2016-04-11 | JP | Mobile App | App icons: After updating from app store, it appears that there are 2 icons |  | Checking | Please remove all then re-install from the Market. It is because of the new update key of the app. [Thang Hong – 17th April] Already explained to client |  |  |  | Images!A72
30 | 2016-04-11 | JP | Mobile App | Remove the setting option on mobile app -- Try it on |  | Finished | Confirmed to remove the setting selection. User can only choose the carat size and diamond cut. Whichever setting the user has chosen previously cannot be changed and will return all other variations of the diamond cut and carat of the chosen setting.  Try it on image will change when user choose the Carat size and Diamond Cut, So user no need to pick any setting any more |  |  |  | Images!A99
31 | 2016-04-11 | JP | Mobile App | Title missing on About JannPaul |  | Checking | Will be updated. |  |  |  | Images!A122
32 | 2016-04-11 | JP | Mobile App | Saved Ring: When delete save ring from the app and restart app, the saved rings are not deleted. |  | Checking | Will be check
33 | 2016-04-11 | JP | Mobile App | Choose your setting: Choose Super Ideal Cut --> swipe to the 3rd pic (yellow gold) - the alignment move. Possible to fixed it. |  | Pending | [SGT:]Could you please explain more details? What does it mean "refer to point 1"? [Thang Hong – 17th April] Alignment problem between pictures which is not smoothly, sometime can, sometime not |  |  |  | Images!A227
34 | 2016-04-11 | JP | Mobile App | Filter page: To replace the cross (arrow pointing) to the word "SAVE", and to have default Diamond Cut to be "open", if not it looks empty. |  | Checking | Will be updated. |  |  |  | Images!A150
35 | 2016-04-11 |  | Mobile App | Additional sent through whatsapp: Point 1: the ring size swiping is too slow to stop Point 2: About JannPaul page - when swipe to next page, the page will "jerk" to go back to the top of the page |  | Checking | 1. The speed of decelerate is set depended on the system OS. Because the ring size circle cover the full page with, it takes time to scroll. Again, the speed is depended on the OS. 2. Please refer to the previous JP's request. The previous request ask us to scroll page to top for changing page.
36 | 2016-04-25 | JP | Mobile App | Filter Page - Currently, if I press reset, it goes back to the choose your setting page automatically. What we prefer is, press reset, the options will "select all", then press save to go back to the choose your setting page. |  | Checking | This behaviour is right, not a bug. Please keep in mind, the current screen is come from the first select diamond cut page. So, since we are here, that means 1 diamond cut has been selected. So, the reset will restore back to the selected diamond cut, not to select all.
37 | 2016-04-25 | JP | Mobile App | Try It on: the ring is missing after taking photo. |  | Checking | This is correct. The default carat condition is 0.5, diamond cut is super ideal. If you do not add enough try it on pictures for the default condition, it will not be shown, because of the 2 conditions. Please add enough try it on images / change the carat / diamond cut to see the according items.
38 | 2016-04-17 | Thang Hong | Mobile App | When I touch on YELLOW GOLD setting, the WHITE GOLD will appear that is something wrong. However this function works if I touch on Explorer button instead of direct touch to the image (pls. see below the ref. example) |  | Checking | Touch on the ring show wrong item details: Will be fixed. |  |  |  | Images!A175
39 | 2016-04-17 | Thang Hong | Mobile App | When I rotate Screen, seem our app does not align.. [Thanh]: I believed I miss answered from HUNG. But my refer is app can be rotate the screen vertically |  | Pending | Rotate the app to landscape mode: Because some screen such as the main screens... are not good to display in the landcape mode, so the app is supported on portrait orientation only. No need to let the app rotate to the landcape mode with JP's designed layout. |  |  |  | Images!A206
40 | 2016-04-17 | jp | Mobile App | I have a request which asked Khiem for long but did not get reply from him. If we update the backend data – how long data will get impact to the app? Possible to change the setting?
1 | 2016-09-26 | jp | Mobile App | Fix picture on TRY IT ON feature |  | finished
2 | 2016-09-26 | jp | Mobile App | Fix carat weight on TRY IT ON feature to show chosen carat from "Choose your setting" page |  | finished
3 | 2016-09-26 | jp | Mobile App | Fix diamond filtering |  | pending | Filter did not work as before. Please follow testcase below for more detail.
4 | 2016-09-26 | jp | Mobile App | Replace header "SAVED RING" to "CHOOSE YOUR SETTING" |  | incorrect change | the ring detail in "SAVED RING" screen was done. The tittle of second page of "CHOOSE YOUR SETTINGS" was changed to: "SAVED RING" --> this change was wrong, please change back like before.
5 | 2016-09-26 | jp | Mobile App | Remove top right hand corner (4 bars icon), user must click back |  | finished
6 | 2016-09-26 | jp | Mobile App | Change text from "your finger or.." to "Choose your proper ring size by aligning the circle with your ring"
|  | Thanh | Mobile App | remove "right arrow" when Ring Size picture change to the last one (Size 61 in Singapore; US size:15.5), the same with Size 1 (remove "left arrow")
App testcase
Android | date: Sep 22
no. | Date Reported | Reported By | Funtions/ Page | Funtions/ Pages decription | CR | Status | Progress/ Resolution | Priority | Responsible by | Delivery Date | Link to Images
1
2
Note on F3: hhthang: if change requesy will be CR else blank
Note on G3: hhthang: Not Started In Progress Testing Completed
Note on I3: hhthang: Critical High Medium Low
Note on J3: hhthang: Mr Thang Mr Tuan Mr Trung
Note on F64: hhthang: if change requesy will be CR else blank
Note on G64: hhthang: Not Started In Progress Testing Completed
Note on I64: hhthang: Critical High Medium Low
Note on J64: hhthang: Mr Thang Mr Tuan Mr Trung

## Images
Images
A15
A47
A72
A99
A122
A150
A175
A206
A227

## CR Bussiness Requirement
jp-M_app Change Request
No. |  | Issue | On | Page | Priority | Change Request?
1 |  | Include an edit function for product variant on backend | Backend | Product variant (Thêm chỉnh sửa detail) | 1 | Yes
2 |  | Fix sharing links to show preview instead of URL | Mobile App | Share | 1 | Yes | Nam
3 |  | Update diamond images on main page | Mobile App | Main page (Diamond) | 2 | Yes | Nam
4 |  | Include a function to select order of product display on backend | Backend | Product variant (Thêm trường ưu tiên) | 2 | Yes
5 |  | Change "Choose your settings, PG2" to Choose Colour | Mobile App/Backend | Choose your setting, Pg2 (Trả về hình màu Slide up, Slide down) | 3 | Yes
6 |  | Try it on picture located on dummy finger
P. Code | Order | Categories | diamondcut | Product Name / tittle | description | setting | Pic | metal | Try it on Pic | carat
item001 |  | Engament Ring | super ideal | Product A | this ring is beautiful | solitaire | 1,2,3,4 | rose gold | Try it on Pic 0.5.png | 0.5
item002 |  | Engament Ring | super ideal | Product B | this ring is beautiful | solitaire | 1,2,3,4 | rose gold | Try it on Pic 1.png | 1
item003 |  | Engament Ring | super ideal | Product C | this ring is beautiful | solitaire | 1,2,3,4 | rose gold | Try it on Pic 1.5.png | 1.5
item004 |  | Engament Ring | super ideal | Product D | this ring is beautiful | solitaire | 1,2,3,4 | rose gold | Try it on Pic 2.png | 2
item005 |  | Engament Ring | super ideal | Product E | ohhh | Diamond Setting | Pic 1,2,3,4 | rose gold | tio A 0.5.png | 0.5
item006 |  | Engament Ring | super ideal | Product F | ohhh | Diamond Setting | Pic 1,2,3,4 | rose gold | tio A 1.png | 1
item007 |  | Engament Ring | super ideal | Product G | ohhh | Diamond Setting | Pic 1,2,3,4 | rose gold | tio A 1.5.png | 1.5
item008 |  | Engament Ring | super ideal | Product H | ohhh | Diamond Setting | Pic 1,2,3,4 | rose gold | tio A 2.png | 2
Gold
Gold
Gold
Gold
Gold
Gold
Gold
Gold

## Sheet1
Vị trí của Try it ring
friendly url show when share
chọn metal khi swipeup / down + thay nút carat = color (metal)
sửa diamond picture phía trước trang choose đầu tiên
backend friendly show,khi vào add sản phẩm phải nhanh, media gọn nhẹ. có thể open trên các thiết bị như ipad dễ chịu.
sửa back end với catagories và easy search product sẽ ảnh hưởng đến các màn hình nào? hướng dẫn 4 step cũng sẽ ảnh hưởng,tên của sản phẩm sẽ ảnh hưởng
cho các thuộc tính như categories metal, carat, setting vào 1 trang setting. xem mô hình quản lý của prestashop
các thuộc tính tạo nên biến thể sản phẩm có thể dùng chung một hình khi trả về qua API.
tất cả các thuộc tính đều có thể sửa trên backend
phần tracking user phải hiển thị ngay tức thì, có thể xuất report: sản phẩm được view nhiều nhất trên app, bảng thông tin người dùng nhanh, tốn ít RAM
app ko nhắc đi nhắc lại đang offline
Priorities order in backend
More value report:
SAVED RING in Backend: can be export to csv or excel ¦ xml --> show the detail: which user saved ring, when, how many time they look on that ring/ how many time they share ring.